## WBS
|  | Working days | Start Date | Delay in days (if any) | Actual Date of completion | Priority | Status
Sprint 1
Front-End Development ( App Design Integration)
Application Design & Creation of modules | Application Design Integration
Sign Up Module
Login Module
Home screen
Feed Display
User Profile Screen
Search Bar
Post Creation
Event screen and sub screens
Groups, Texts & Notifications
Press to Talk Button
SOS Button ( Emergency Assistance )
Navigation screen
Accident Reporting screen and subscreens
Weather Information screen and Trip Planning screen
Feedback and Ratings screens
Settings Screen
Demo 2 | This demonstration for design integration of application
Sprint 2
Back-End Development
User Registration Functionality | Ability for the user to register/create an account to the application via social media ( google, facebook and apple id) or Mobile Number with OTP | 1 day if the frontend completes the authentication from his end | whenver I get affirmation from the frontend | 1 extra day |  | A
User Login Functionality | Ability for the user to login to the application via social media ( google, facebook and apple id) or Mobile Number with OTP | same day when I work on register | same as above | 1 extra day |  | A
API creation | API creations for all the application modules | 5 to 7 days | started, 17-09-2023 | 2-3 days |  | B
API integration | Based on modules apis will be integrated in the application | Will have to check how MapIndia library works then only I can tell the time | 2023-09-19 | a week |  | C
Third part API integration | All the third party api integration in the application |  | 2023-09-20 |  |  | C
Database structure changes | Database sctructure changes as per current back end developement |  | 2023-09-21 |  |  | B
Cronjob | For live updates |  |  |  |  | B
Demo 3 | This demonstration for application functionality
Sprint 3
Admin Panel
Admin Registration functionality | Super admin will add other admins via using invite email link | 2 days |  |  |  | A
Admin user onboarding | Super admin will verify the admin user and verified users will have blue tick | same day when I work on admin registration functionality |  |  |  | C
| Aadhar Card / Pancard based verification will be done for admin users |  |  |  |  | A
Dashboard | Admin shall be able to view following information on dashboard ○ Total no. of active and inactive registered buyers ○ Total no. of Products uploaded on website ○ Total Revenue: today/ this month | a week |  |  |  | C
Event Management | Administrators can manage events, including creating, editing, and deleting events. | 2 days |  |  |  | A
User Management | Administrators can manage user accounts, including creating, editing, and deleting accounts |  |  |  |  | B
Car Management | Administrators can manage follower cars, including adding, editing, and removing cars from the application. | same day when I work on user management |  |  |  | B
Content Management | Administrators can manage content on the application, such as event descriptions, safety guidelines, and other informational texts. | a week |  |  |  | A
Notification Management | Administrators can send push notifications to users, such as event updates, important announcements, or emergency alerts |  |  |  |  | C
Analytics & Reports | Administrators can access analytics and generate reports related to user engagement, event participation, and application usage. | 3-5 days |  |  |  | C
Demo 3 | This demonstration for admin panel work
Sprint 4
UAT & Deployment
UAT | Entire application testing
Demo 4 | Final update will be share with client
Deployment | After finalization app will be deployed to client's server